## Sheet1
CITS3200 Project Billed Hours Record for <Camilo Lima Castillo> Each time you do some work on the project, note the week number, start and end date and hour, plus a brief description of the activity. At the end of each week send a copy of the sheet as it currently stands to your group's manager for recording on the group TimeSheet. Date in the form DD/MM/YY and time as XX:YY (24hr clock)
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours
| Date | Time | Date | Time
5 | 2024-08-23 | 17:00 | 2024-08-23 | 18:00 | Mentor Meeting | 1 | 1 | 1
5 | 2024-08-22 | 17:00 | 2024-08-22 | 18:00 | Group meeting | 1 | 2 | 1
5 | 2024-08-24 | 18:00 | 2024-08-24 | 19:00 | Satus Update Deck | 1 | 3 | 1
6 | 2024-08-28 | 11:00 | 2024-08-28 | 12:00 | Client Meeting | 1 | 4 | 1
6 | 2024-08-29 | 17:00 | 2024-08-29 | 18:00 | Group meeting | 1 | 5 | 1
6 | 2024-08-27 | 17:00 | 2024-08-27 | 17:45 | Client Status Update Deck | 0.75 | 5.75 | 0.75
7 | 2024-09-12 | 17:00 | 2024-09-12 | 17:30 | group meeting | 0.5 | 6.25 | 0.5
7 | 2024-09-11 | 11:00 | 2024-09-11 | 11:30 | Client Meeting | 0.5 | 6.75 | 0.5
7 | 2024-09-13 | 19:00 | 2024-09-13 | 21:00 | Pandas Research | 2 | 8.75 | 2
7 | 2024-09-13 | 21:00 | 2024-09-13 | 22:00 | Prototype Testing | 1 | 9.75 | 1
8 | 2024-09-17 | 20:00 | 2024-09-17 | 21:00 | Pre-demo meeting | 1 | 10.75 | 1
8 | 2024-09-17 | 17:30 | 2024-09-17 | 20:00 | Error detection development | 2.5 | 13.25 | 2.5
8 | 2024-09-18 | 11:00 | 2024-09-18 | 12:00 | Demonstration meeting (sprint 2) | 1 | 14.25 | 1
8 | 2024-09-18 | 12:00 | 2024-09-18 | 13:00 | Sprint 2 development meeting | 1 | 15.25 | 1
8 | 2024-09-18 | 16:00 | 2024-09-18 | 23:00 | Front end research and development | 7 | 22.25 | 7
8 | 2024-09-19 | 17:00 | 2024-09-19 | 18:00 | Group meeting | 1 | 23.25 | 1
8 | 2024-09-19 | 18:00 | 2024-09-19 | 20:00 | Research and timesheeting | 2 | 25.25 | 2
8 | 2024-09-20 | 17:00 | 2024-09-20 | 20:00 | Front end development | 3 | 28.25 | 3
9 | 2024-09-23 | 19:00 | 2024-09-23 | 20:00 | Front end development | 1 |  | 1
9 | 2024-09-25 | 11:00 | 2024-09-25 | 11:20 | client meeting | 0.33333 | 0.33333 | 0.33333
10 | 2024-10-03 | 17:00 | 2024-10-03 | 18:30 | group meeting | 1.5 | 1.8333 | 1.5
10 | 2024-10-05 | 11:00 | 2024-10-05 | 14:00 | front end work and back end integration | 3 | 4.8333 | 3
11 | 2024-10-07 | 18:00 | 2024-10-07 | 21:00 | backend api integreation testing | 3 | 7.8333 | 3
11 | 2024-10-09 | 11:00 | 2024-10-09 | 11:30 | Client Meeting | 0.5 | 8.3333 | 0.5
11 | 2024-10-10 | 17:00 | 2024-10-10 | 18:00 | group meeting | 1 | 9.3333 | 1
11 | 2024-10-12 | 8:00 | 2024-10-12 | 17:00 | Front end refactor, development and implementation | 9 | 18.3333 | 9
11 | 2024-10-12 | 19:00 | 2024-10-12 | 22:00 | Front end development and implementation | 3 | 21.3333 | 3
12 | 2024-10-13 | 16:30 | 2024-10-13 | 18:00 | auditor meeting and project admin | 1.5 | 22.8333 | 1.5
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0